## Slide 1
Rev. July 2015
CANADEM
Operations Gaming
of activities and contingency plans
Like a SWOT analysis, Operations Gaming is a heuristic technique to stress test a course of action (COA), ranging from intended activities to contingency plans.
The aim is to assess:
  if current risk mitigation measures, e.g. contingency plans, are sufficient;
  Identify risks not currently being considered
PROCESS: in sequential stages following the COA timeline.
PLAYERS: Usually two sides and a referee:
  The Primary(ies) planning to carry out a COA/mission/project at each stage will describe what they will achieve at that stage;
  Disrupter(s) who at each stage will respond and challenge assumptions and expectations with realistic risks (‘what-if’s);
  A Referee will facilitate and arbitrate.
Notes: Operations Gaming is a structured role-playing exercise in which the key individuals planning to carry out a mission or project are challenged by ‘disrupters’ who raise every conceivable risk in an effort to show that they are not prepared for all contingencies.

## Slide 2: Most courses of action (COAs) will have many separate actions/stages, therefore: 1. there will be many Op-Game rounds, e.g. one for each decisive point; 2. the initial Primary statement in each round is quite brief 3. the disruptor’s challenge and primary’s response may be short statements, or could become a back and forth dialogue/argument arbitrated by the referee.
We will build a garage beside our house for our new Porsche before winter arrives.
We have the building permit
We think we can get a loan (will follow-up on this)
Contingency plan (AKA branch-plan): our neighbor Ted said we can use his garage this winter.
Primary’s initial statement
Disrupter’s challenge
Primary’s response
1. You will not get a
building permit;
2. You will run out of money;
3. A forest fire will burn it
down.
Referee says #3 is so
unlikely that primary
doesn’t need to respond
to that risk.
The referee signals the end of this round; records the ‘results’; and moves on to the next round.
Sample OP-Game single round

## Slide 3: Each Ops Game is unique and dynamic:
Every ops game is different depending on variables such as the complexity of a COA; the number, likelihood and impact of risks; the time available to ops game; and the results needed e.g. foolproof or good-enough.
Usually the COA Primary will convene key participants to agree to stages, timing, goals, and select a strong knowledgeable disrupter team who will prepare their challenges.
As it is a heuristic exploration of what could go wrong and whether the organization is sufficiently prepared, there should be latitude as to the agreed process, and flexibility on how the referee facilitates that process so as to not inhibit relevant brainstorming and debate.

## Slide 4: Role of Referee / Facilitator
This is a contest between
the disruptor-team with their challenges trying to show how the organization generally and the primary specifically is not fully prepared for risks and eventualities; and
the primary-team looking to show they are prepared, or not, and so need to do more risk mitigation.
During the ops game, the referee will
  Facilitate: stay on topic, on time, and let all speak.
  Referee: judge challenges to be realistic, responses to be sufficient for the time being.
  Record: possibly using an assistant, capture salient aspects, particularly new risks or seeming insufficient mitigation of known risks.

## Slide 5: Results
Reassure the Primary and management that all of the risks have been identified and sufficiently mitigated; or
Enable CANADEM to identify new risks, or known risks that are not sufficiently assessed and/or mitigated. That fuller assessment and mitigation will occur after the op gaming, so the referee will record that there is required follow-up, and keep the game rolling.

## Slide 6: Note to non-CANADEM
Of course, feel free to use this powerpoint, and adapt it for your use. We hope it is useful.
Try watching it in presentation mode, as some slides have ‘builds’ that you might find useful.
CANADEM’s in-house powerpoint is more extensive.
If you are interested in contracting CANADEM to help you customize this presentation or provide training assistance, please contact
Paul.LaRose-Edwards@CANADEM.ca